## Historical load
Color | Meaning | Table | Feed File | Assigned to | Notes | Andrea
| Done | DimDate | Date.txt | Dimitris |  | Dimitris
| Assigned | DimTime | Time.txt | Uche |  | Hridaya
| Unassigned | Industry | Industry.txt | Uche |  | Uche
|  | StatusType | StatusType.txt | Uche
|  | TaxRate | TaxRate.txt | Uche
|  | TradeType | TradeType.txt | Uche
|  | DimBroker | HR.csv | Dimitris
|  | DimCompany | FINWIRE | Dimitris
|  | Financial | FINWIRE | Uche | Similar implementation with DimCompany
|  | Prospect | prospect.csv | Uche
Audit
|  | DimCustomer | CustomerMgmt.csv | Dimitris | Still need to reflect the changes fo DimCustomer to DimAccount
|  | FactHoldings | HoldingHistory.txt | Hridaya
|  | FactCashBalances | CashTransaction.txt | Hridaya
|  | DimAccount | CustomerMgmt.csv | Dimitris
|  | DimSecurity | FINWIRE | Dimitris