## Historical load
Color | Meaning | Table | Feed File | Assigned to | Notes | Andrea
| Done | DimDate | Date.txt | Dimitris |  | Dimitris
| Assigned | DimTime | Time.txt | Uche |  | Hridaya
| Unassigned | Industry | Industry.txt | Uche |  | Uche
|  | StatusType | StatusType.txt | Uche
|  | TaxRate | TaxRate.txt | Uche
|  | TradeType | TradeType.txt | Uche
|  | DimBroker | HR.csv | Dimitris
|  | DimCompany | FINWIRE | Dimitris
Industry
|  | Financial |  |  | Similar implementation with DimCompany
Prospect
Audit
|  | DimCustomer |  | Dimitris | Still need to reflect the changes fo DimCustomer to DimAccount and implement the INACT property
|  | FactHoldings | HoldingHistory.txt | Hridaya
|  | FactCashBalances | CashTransaction.txt | Hridaya